## Intake Form
IAS Project Intake
Submission Date |  | 2022-02-16 | [13 empty] | Approved
Project Title |  | CloudMed DRG Validation & Underpayment Implementation | [8 empty] | Strata # |  |  |  |  | Rejected
[11 empty] | IAS SN # |  |  |  |  | Hold
Project Description |  | Accurate DRG selection & payer payment according to contract are critical to maximized revenue. Implementing CloudMed's DRG Validation & Underpayment Services is expected to increase revenue by $1M-$7M annually. 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget. | [13 empty] | Other
[8 empty] | Business Sponsor |  |  | Underpays, D. Lauten; DRG Val, G. DiCrocco
[8 empty] | IAS Project Sponsor |  |  | Robert Oliver
[9 empty] | Discovery Meeting Date |  |  | 2022-02-04 |  |  |  | Yes
Requested |  | Deliver necessary technical enablers based on CloudMed's implementation plan, and support Operations to ensure smooth operationalization of tech enablers. | [6 empty] | Proposed Start Date |  |  | 2022-02-01 |  |  |  | No
IAS Services | [8 empty] | Proposed Go Live Date |  |  | 2022-05-01
[9 empty] | Proposed End Date |  |  | 2022-09-01
Sustaining Functionality
|  | No |  |  | New Product / Service | Yes |  |  | Project is Mandated | No |  | Impact | Medium
[5 empty] | Enhancement to Existing P/S | No |  |  | (Regulatory or Compliance) |  |  | Risk | 16
Governing Committee |  |  | CEO Council (CEOC) | [8 empty] | T-Shirt | L
Project Outcomes |  | Implement CloudMed services by May 2022 and begin realizing additional revenue by July 2022, for a total of $500k for each service in 2022.
Project Justification |  | 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget.
Risk Analysis - Risk of not doing | [5 empty] | Category |  | Probability |  | Impact |  | Risk Score |  | Probability | Impact
Negative Budget Variance of $1M | [5 empty] | Business |  | Likely |  | Major |  | 16 |  | 4 | 4
[12 empty] | 0 |  | N/A | N/A
[12 empty] | 0 |  | N/A | N/A
Project Funding |  |  | Grant |  | No |  |  | Grant Name
Is funding needed? |  |  | Amount
No
Fiscal Year Carry Over |  |  | Business OpEx |  | 0 |  | IAS OpEx |  | 0 |  |  | Other Expenses
No |  |  | Business CapEx |  | 0 |  | IAS CapEx |  | 0 |  |  | 0
Support Funding |  | Fiscal Year 1 (Project) |  | Fiscal Year 2 |  | Fiscal Year 3 |  | Fiscal Year 4 |  | Fiscal Year 5 |  | Total
IAS OpEx
| Maint/ License | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Services | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Hardware | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IAS CapEx |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Combined Yearly | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
IAS Opinion |  | IAS concerns or issues with project or work effort
|  | PHI Implications |  |  |  | PCI Implications |  | FISMA Implications |  |  |  | IAS Annual
Support Hours
|  | Hosted Services |  |  |  | IAS Standards Compliant |  |  | IPT Involved
IAS Reviews Completed |  |  | Data |  |  | Technical |  |  | Security |  |  | Applications
IAS Reviews Satisfactory |  |  | Data |  |  | Technical |  |  | Security |  |  | Applications
Vendor Utilized |  | CloudMed | [9 empty] | Existing Relationship | Yes
Decision Authority | [8 empty] | Decision
| (Individual or Committee) | [7 empty] | Decision Date
Comments |  | To be completed by IAS Project Review Committee indicating if the project is approved or not.
Note on N15: Calculated score
Note on N16: Calculated score
Note on N18: Calculated score

## Submission Data1 (hidden)
Project Submission Form
Project: | CloudMed DRG Validation & Underpayment Implementation | Project #:
Project Manager: |  | Sponsor: |  | Customer Based Data
Project Artifacts: |  | Last Update:
Background (Statement of Problem) |  |  |  | The "problem" AFFECTS…... (Users / stakeholders]…Who specifically is impacted?
Business need |  |  |  | the IMPACT of which is…. Statement of issues, costs, or other impacts]… Lacking a solution what are the impacts and outcomes suffered as a result of the business problem? (In other words, what’s the business driver; why may the company be compelled to solve the problem?)
Objectives (What is to be achieved) |  |  |  | A SUCCESSFUL SOLUTION would be …...(Important benefits that would successfully solve the problem). What characteristics and qualities does an acceptable and/or compelling product / solution include? What would a (generic) product / solution do or have that addresses or resolves key issues and needs
Scope | In Scope | Out of Scope |  | Solution Value
Describe Value in terms of increased clinical, patient, or business value inside and outside WFBH.
Deliverables (Deliverables and Associated Key Milestones) | Deliverable |  | Deliverable / Key Milestone Target Dates
Kick-Off
Identification of key metrics for measuring success of implementation and/or usage.
Design/Build
Go-Live
Value Options
Is this request to replace existing software? If yes, why is your current software inadequate? Describe: Feature / function short comings, or express operational impacts / failures resulting from the existing software.
Vendor |  |  | Vendor Solution (Product/ Component) Name(s)
Vendor Contact
Is there any interim value that can be provided prior to the product / service delivery? Express any additional value that could be achieved with existing owned business capabilities prior to purchase or delivery. Answer the question, if the purchase is delayed or not approved how will you gain value until purchase of the product / service? Identification of key metrics for measuring interim success are helpful
General Contract Terms
Signatures
Business Sponsor |  |  |  | What will be the impact(s) of the application / product to clinical operations?
Signature
|  |  |  | Positive Impacts to clinical operations: How does the application / solution the operations environment in which it will operate? | Negative Impacts / Risks to clinical operations: How does the application / solution negatively affect the operations environment in which it will operate? Are there any risks with the product in an operations environment? | Success Criteria
Printed Name
Date
ITS Sponsor
Signature
Printed Name
Date
Note on D21: Note A for assumptions, C for constraints
Note on E22: This is a field you can use to identify risks by categories such as technological, personnel, etc.

## Submission Data - 1
Project Submission Form
Project: | CloudMed DRG Validation & Underpayment Implementation |  | Project #: | 0
Project Manager: |  |  | Business Sponsor: | Underpays, D. Lauten; DRG Val, G. DiCrocco
Background (Statement of Problem) | Accurate DRG selection & payer payment according to contract are critical to maximized revenue. Implementing CloudMed's DRG Validation & Underpayment Services is expected to increase revenue by $1M-$7M annually. 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget.
Business need | 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget.
Objectives (What is to be achieved) | Implement CloudMed services by May 2022 and begin realizing additional revenue by July 2022, for a total of $500k for each service in 2022.
Scope | In Scope |  |  | Out of Scope
DRG Validation - Data Spec, scheduled for recurring submission via sFTP drop
Underpayments - Data Spec (same as above, + Epic Application build
i.e. WQ's, Claim Edits, Billing Indicators, etc
May change after Ops designs future state once IT approval and kick-off can occur
Deliverables (Deliverables and Associated Key Milestones) | Deliverable |  |  | Deliverable / Key Milestone Target Dates
| Kick-Off |  |  | 2022-02-28
| Payer Contracts provided and loaded |  |  | 3/7-4/4
| ITS Build |  |  | 3/7-4/15
| Ops Design |  |  | 3/7-4/15
| Testing |  |  | 4/16-4/30
| Training |  |  | 4/16-4/30
| Go-live |  |  | 2022-05-01
| Revenue Realization Begins |  |  | 2022-07-01
| Project Closure - operationalization |  |  | 2022-09-01
This is current draft of timeline, given project is still in Initiation Phase
Hard dates are Go-live and revenue realization dates
Vendor | CloudMed |  |  | Vendor Solution (Product/ Component) Name(s)
Vendor Contact | Justin Licht <Justin.Licht@cloudmed.com>
General Contract Terms | Exisiting Contract |  |  | New Contract
Start Date | Check with Atrium IAS
End Date
Terms of Contract
Signatures
Business Sponsor
Signature
| Printed Name | Underpays, D. Lauten; DRG Val, G. DiCrocco
Date
IAS Sponsor
Signature
| Printed Name | Robert Oliver
Date

## Submission Data - 2
Customer Based Data
The "problem" AFFECTS…... (Users / stakeholders]…Who specifically is impacted? | Every employee in AHWFB
the IMPACT of which is…. Statement of issues, costs, or other impacts]… Lacking a solution what are the impacts and outcomes suffered as a result of the business problem? (In other words, what’s the business driver; why may the company be compelled to solve the problem?) | Accurate DRG selection & payer payment according to contract are critical to maximized revenue. Implementing CloudMed's DRG Validation & Underpayment Services is expected to increase revenue by $1M-$7M annually. 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget. This project critical to increasing AHWFB's margin. Without this project, margin target may not be hit. If 1% is not achieved, then each employee does not get additional 1% employer base retirement contribution which is contingent on > 1% margin
A SUCCESSFUL SOLUTION would be …... (Important benefits that would successfully solve the problem). What characteristics and qualities does an acceptable and/or compelling product / solution include? What would a (generic) product / solution do or have that addresses or resolves key issues and needs | Implemented by 5/1/2022 and realizing additional revenue by 7/1/2022
Solution Value
Describe Value in terms of increased clinical, patient, or business value inside and outside WFBH. | Accurate DRG selection & payer payment according to contract are critical to maximized revenue. Implementing CloudMed's DRG Validation & Underpayment Services is expected to increase revenue by $1M-$7M annually. 2022 AHWFB Budget expects $500k for both. If not implemented by May 2022, this revenue will be delayed & cause negative variance to budget.
Identification of key metrics for measuring success of implementation and/or usage. | Underpayment Recoveries as % NPSR DRG Improvement as % IP Payments Baselines on both have been determined
Value Options
Is this request to replace existing software? If yes, why is your current software inadequate? Describe: Feature / function short comings, or express operational impacts / failures resulting from the existing software. | Operating as secondary behind current vendors (STAT Rev for Underpayments and Enjoin for DRG Validation)
Is there any interim value that can be provided prior to the product / service delivery? Express any additional value that could be achieved with existing owned business capabilities prior to purchase or delivery. Answer the question, if the purchase is delayed or not approved how will you gain value until purchase of the product / service? Identification of key metrics for measuring interim success are helpful | We have already engaged in recurring performance meetings with existing vendors through PFS VMO. This has driven up Enjoin performance by $10.6M since January 2020. however, improvement is leveling out, indicating need for other effort.
What will be the impact(s) of the application / product to clinical operations?
Positive Impacts to clinical operations: How does the application / solution the operations environment in which it will operate? | Negative Impacts / Risks to clinical operations: How does the application / solution negatively affect the operations environment in which it will operate? Are there any risks with the product in an operations environment? | Success Criteria
Critical that one Project Manager oversees all aspects of implementation (this is PFS PM, with insight into IT)
More revenue means more investment in clinical operations | None | Critical that ITS identify resources to complete build and engaged in kick-off.
IT PM would help with IT work coordination

## Impact Scoring
Impact Scoring
| Low Impact (1) | Medium Impact (3) | High Impact (5) | Rating | Weight | Score
Departments | One | One to Two | At least three. Cross-functional team required | 5 | 3 | 15
Complexity | Simple, requirements should be understood through an email | Requirements should be understood by IAS through one meeting involving one or two customers | Requirements need to be gathered through multiple meetings with a variety of stakeholders throughout campus | 5 | 3 | 15
Resolution Time | < 80 managed hours | 80-480 managed hours | >480 managed hours | 3 | 3 | 9
Deadline | Flexible. Low impact | Somewhat flexible. Some impact | Fixed. Significant impact | 5 | 3 | 15
Cost | Uses existing resources. No additional budget | Requires budget up to $49,999 | Budget at least $50,000 | 1 | 3 | 3
Resource Scarcity* | No competing requests. Little to no impact on scarce resources | Resource limited. Increased analysis and consideration of alternatives | Resource intensive. Significant impact | 3 | 5 | 15
Risk / Visibility | Low Risk. Project can revert to prior state easily. Little to no negative impact on stakeholders | Moderate risk. Project can revert back with some downtime and loss of use. Failure may create moderate inconvenience and visibility | High risk. High visibility. Significant impact on work processes. | 5 | 5 | 25
Funding | The project is completely funded. |  | The project is not completely funded. | 1 | 5 | 5
Patient Outcomes | Does not affect patient outcomes | Indirectly affects patient care, outcome. | Improves patient care, outcome, and safety at all sites. | 1 | 5 | 5
Compliance/Contractual | No contractual obligations or compliance impact | Minor contractual obligation or compliance issue | Major contractual obligation or compliance issue | 3 | 5 | 15
Ongoing Costs | Negligible impact on staff to maintain with minimal budget impact | Some impact on staffing less than 5 FTE to support with budget impact less than $100K | Significant impact on staffing more than 5 FTE to support with budget impact over $100K | 1 | 5 | 5
*Resource scarcity can include key project participants with impacted schedules or new technology requiring skills and experience not currently available to the project team.
Impact Score Range |  | Impact Score | 127
Low Impact | 45-100 | Impact | Medium
Medium Impact | 100-175
High Impact | 175-225

## Business Outcome BR Pathway
Technology Request Benefits Realization Template
Request
CloudMed DRG Validation & Underpayment Implementation
Business Outcome Benefits Realization Pathway | Business Strategy | Goals & Objectives | Key Business Objectives | Key Performance Indicators | Operational Indicators | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
| What is to be accomplished? | What are the Goals and objectives that will be realized with the strategy? | What are the most important actionable steps to met he goals and objectives? | What measures of success are tied to the drivers? | Define operational Metrics | Underpayment Recovery | Underpayment as % NPSR | 0.053% | 0.07% | 2022-07-01 | C. Brown
Define operational Metrics
Define operational Metrics
|  |  | Key Business Objectives | Key Performance Indicators | Financial Indicators | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
|  |  | What are the most important actionable steps to met he goals and objectives? | What measures of success are tied to the drivers? | Define Financial Metric | DRG Improvement | DRG Improvement as % IP Payments | 0.61% | 1% | 2022-07-01 | C. Brown
Define Financial Metric
Define Financial Metric
|  |  | Key Business Objectives | Key Performance Indicators | Strategic Indicators | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
|  |  | What are the most important actionable steps to met he goals and objectives? | What measures of success are tied to the drivers? | Define Strategic KPI | Underpayment Recovery | Underpayment as % NPSR | 0.053% | 0.07% | 2022-07-01 | C. Brown
Define Strategic KPI
Define Strategic KPI

## Business Change BR Pathway
Technology Request Benefits Realization Template
Request
CloudMed DRG Validation & Underpayment Implementation
Business Change Benefits Realization Pathway |  |  |  |  | Growth of Business | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
| Business Problem | Change | Benefit | Benefit Indicators
| What is the current business problem? | What has to change within the business? | What is the benefit of change? | What measures are indicators of change? | Define Growth Metrics
Define Growth Metrics
Define Growth Metrics
[5 empty] | Transformation of Business | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
|  |  | Benefit | Benefit Indicators
|  |  | What is the benefit of change? | What measures are indicators of change? | Define Transformation Metrics
Define Transformation Metrics
Define Transformation Metrics
[5 empty] | Running of Business | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
|  |  | Benefit | Benefit Indicators
|  |  | What is the benefit of change? | What measures are indicators of change? | Define Business / Operational Metrics
Define Business / Operational Metrics
Define Business / Operational Metrics

## Process Outcome BR Pathway
Technology Request Benefits Realization Template
Request
CloudMed DRG Validation & Underpayment Implementation
Process Outcome Benefits Realization Pathway
| Business Impact | Processes | Process Input | Process Activities | Process Outcomes
| What business capabilities are impacted? | What is a key process associated with capabilities? | What are the resource contribution changes? | What work is conducted to achieve objectives & Activities directly linked to outcomes? | What are the product or service delivered?
[6 empty] | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
Resource Productivity
Resource Volumes
Process Effectiveness
Process Reliability
Process Cycle time
Process Cost
Process Compliance
Process Quality
Product / Service Cost
Process Outcomes
|  | Processes | Process Input | Process Activities
|  | What is a key process associated with capabilities? | What are the resource contribution changes? | What work is conducted to achieve objectives & Activities directly linked to outcomes? | What are the product or service delivered?
[6 empty] | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
Resource Productivity
Resource Volumes
Process Effectiveness
Process Reliability
Process Cycle time
Process Cost
Process Compliance
Process Quality
Product / Service Cost
Process Outcomes
|  | Processes | Process Input | Process Activities
|  | What is a key process associated with capabilities? | What are the resource contribution changes? | What work is conducted to achieve objectives & Activities directly linked to outcomes? | What are the product or service delivered?
[6 empty] | Measure Defined | Unit of Measure | Baseline Measure | Target Measure | Timeframe to Achieve | Responsible Party for Measure
Resource Productivity
Resource Volumes
Process Effectiveness
Process Reliability
Process Cycle time
Process Cost
Process Compliance
Process Quality
Product / Service Cost

## Resource Estimates
IAS to fill out - IAS Resource Estimates
Resource Estimates by Assignment Group - Hours by Month
Assignment Group | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Total Hours
Data Management - Analytics | 2022-02-01: 20; 2022-03-01: 40; 2022-04-01: 40; 2022-05-01: 10; 2022-06-01: 5; 2022-07-01: 5; 2022-08-01: 5; 2022-09-01: 5 | 130
InfoSec - EPIC Access and Security | 2022-03-01: 5; 2022-04-01: 5; 2022-05-01: 5 | 15
Hospital Based Billing | 2022-02-01: 0; 2022-03-01: 80; 2022-04-01: 80; 2022-05-01: 30; 2022-06-01: 5; 2022-07-01: 5; 2022-08-01: 5; 2022-09-01: 5 | 210
ITS-PMO | 2022-02-01: 0; 2022-03-01: 5; 2022-04-01: 5; 2022-05-01: 5 | 15
Data Management - Data Integration | 2022-03-01: 10; 2022-04-01: 10; 2022-05-01: 5 | 25
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Hours | 0 | 20 | 140 | 140 | 55 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395
Note on B3: Enter the first date of the month the project will start.

## Change Request (hidden)
PROJECT CHANGE REQUEST FORM
Change Request Number |  | Project # |  | Date:
Project Name:
Project Manager:
Business Sponsor:
Change Details
Change Requested By:
Email Address:
Contact Number:
Location:
Reason For Change:
Change Impact Analysis
Action
(How/What/Where/When?)
Number of people responsible for carrying out change/ impact analysis:
How will this Change affect the following?
Delivery Date: | Cost: |  | Schedule: | Scope:
Authorization
Expenditure Approved |  |  | Approved
Sponsor Sign Off: |  |  | ITS Sign Off:
Change Close-Out
Follow up Comments:
Has appropriate and effective action been implemented?
Business Sponsor Name:
Project Manager Name:

## Hidden (hidden)
Committees | Assignment Groups
IT Steering Committee (ITSC) | 3M
CEO Council (CEOC) | Academic Applications (Education)
Chief Medical Officers (CMO) | Academic Applications (Research)
Ambulatory Systems
ARB
Beaker
Cadence
ClinDoc
Clinical Device Integration
Clinical Research
Collaboration Services
Configuration Management
Core Client Services
Cornerstone AMB
Data Management - Analytics
Data Management - Application Development
Data Management - Data Archive
Data Management - Data Integration
Database Administration
Datacenter Operations
Davie Region
EIO Refresh Team
Emergency Services
Enterprise Applications
Enterprise Architecture
Enterprise Storage
Epic Data Courier Clarity
Epic Technical
Facilities Administration
Grand Central/Prelude
High Point Region
HIM (ITS)
Hospital Based Billing
Hospital Based Claims
Imaging Systems Cupid
Imaging Systems PACS
Imaging Systems Radiant
InfoSec - Business Continuity
InfoSec - Cybersecurity
InfoSec - EPIC Access and Security
InfoSec - FISMA
InfoSec - Identity and Access
InfoSec - Payment Card Services (PCI)
InfoSec - Risk and Compliance
InfoSec-Threat and Vulnerability Managem
IP Orders
IT Hardware Logistics & Equipment Dispos
IT Service Management
ITS Accounting and Finance
ITS Clinical Informatics
ITS-PMO
Lexington Region
Messaging Services
Multimedia
Network Engineering
Nursing Informatics
OnBase
Oncology (Beacon)
Perioperative
Pharmacy (Willow)
Professional Billing
Professional Billing Claims
Quality MU
Radiation Oncology
Research Technology Support
Server Operations
Shared Services Applications
Student Technical Support
Telecommunications
Unix/Linux Server Admin
Vendor Management
Virtual Health Services
WakeOne Training
Wilkes Region
Winston Region
Winston Region - OR Technical Support
Wireless